## Proje Planlayıcısı
Design of a Hex
[8 empty] | 2021-01-15 |  |  | Plan Süresi | [16 empty] | Fiili (planın ötesinde) | [7 empty] | % Tamamlandı (planın ötesinde)
Task Packages | Tasks | Task Distribution |  |  |  | Task Start | Task Interval
|  | Deniz Germen | Işıl Aybar | Berkay Çırak | Doğuş Karataş |  |  | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11
Constraint Evolution | Gant Chart | x | x | x | x | 2020-12-18 | 1
| Heat Duty | x | x | x |  | 2020-12-19 | 1
| Temperature Profile | x | x | x | x | 2020-12-19 | 1
| Location | x | x | x | x | 2020-12-19 | 1
Preliminary Design | Literature Search for Design | x | x | x | x | 2020-12-20 | 3
| Gasket and Plate Material Selection |  |  | x |  | 2020-12-23 | 1
| Constant Determintion | x | x |  | x | 2020-12-23 | 1
Design | Contructional Data Evaluation | x | x | x | x | 2020-12-24 | 4
| Cost Relations |  |  | x |  | 2020-12-28 | 1
| Optimization Path Sekection | x | x |  | x | 2020-12-29 | 2
| Sample Calculations | x |  | x |  | 2020-12-31 | 2
| Algotiyhm, Coding | x |  |  |  | 2021-01-02 | 6
| Sync Control | x | x |  | x | 2021-01-08 | 1
| Result Evoluation | x | x | x | x | 2021-01-09 | 2
| Report; Format, Check | x | x | x | x | 2021-01-11 | 4